## Slide 1: Bi-weekly Capstone Project Progress Meeting Guidelines DSC 383W / 483: Data Science Capstone Spring 2020

## Slide 2: Team Meeting Preparation (held every ~2 weeks)
Review progress against project charter milestones
Few slides to showcase latest results/tasks
Outline next steps
Discuss any concerns
Task | Target date | Actual Date | Status
Data Access complete | 10/15/2019 | 10/8/2019 | Complete
Exploratory analysis completed | 10/27/2019 |  | In Progress
… | … |  | 
First iteration of model completed | 11/5/2019 |  | 

## Slide 3
Objectives (Copy from Project Charter)
Challenges
Achievements / Contributions (per team member)
Next Steps
Create couple of slides to explain each of the boxes below
(details on subsequent slides)

## Slide 4: Presentation Template
Objectives
Objectives usually remain the same throughout the project.
They are typically agreed to with the sponsor at the beginning of the project.
Yet, it is good to have them handy to remind you of the goal periodically !!
Of course, adjustments are allowed but have to be agreed to with the sponsors.

## Slide 5: Presentation Template
Achievements
In this section the team talks about what has been done since the last meeting, and each team member shows his or her portion.
Typically, this section answers to the Next Steps section in the previous report. We will focus on the team’s progress against tasks it listed as the next steps in the previous meeting.
Also, a good time to bring up deviations from the tasks (plan) proposed previously …more on next slide

## Slide 6: Presentation Template
Next Steps
In this section, the team lists the tasks it expect to complete by the next meeting.
If there exist some unfinished tasks due to challenges, also address the plans on how to resolve such challenges (i.e. keep tackling it or try different approaches)

## Slide 7: Presentation Template
Challenges
Talk more in detail about challenges encountered during progress since last meeting, and how they are resolved.
If some challenges are not resolved in time, give the reasons and the updated plan
Challenges are expected but important for the team to brainstorm and address it (for example, some tasks turned out to be more difficult than imagined and thus require more time).